ERP SYSTEM

Project Implementation Roadmap & Milestones

10-Week Implementation Timeline
(May 28, 2026 - August 6, 2026)

Project: ERP for Small & Medium Stores
Version: 1.0.0
Team: 1 Developer (Full-Stack)
Environment: Development (Windows)
Technology: Java 17, Spring Boot 3.1.5, React, PostgreSQL 15+

Complete Project Roadmap with Phases, Tasks & Milestones

# Table of Contents

1. Project Overview & Goals

2. High-Level Roadmap (10 Weeks)

3. Phase 1: Foundation (Weeks 1-2)

4. Phase 2: Core Backend (Weeks 3-5)

5. Phase 3: Frontend Development (Week 6)

6. Phase 4: Integration & Testing (Week 7)

7. Phase 5: Optimization & Deployment (Weeks 8-9)

8. Phase 6: Finalization & Go-Live (Week 10)

9. Milestone Tracking & Success Criteria

10. Risk Management & Contingency

# 1. Project Overview & Goals

Project Name: ERP System for Small & Medium Stores
Scope: Single Tenant (Local) with Multi-Tenant Ready Architecture
Start Date: May 28, 2026
Target Go-Live: August 6, 2026 (10 weeks)
Team Size: 1 Full-Stack Developer
Target Users: 2-6 concurrent users (scalable to enterprise)

Primary Objectives:
1. Develop a functional ERP system with all core modules
2. Support Arabic and English interface
3. Implement secure authentication and role-based access
4. Generate professional invoices with tax compliance
5. Create comprehensive reporting suite
6. Deploy on local PostgreSQL database
7. Ensure system stability and performance
8. Document for knowledge transfer

Success Criteria:
✓ All core modules operational (Sales, Inventory, Accounting)
✓ User authentication & authorization working
✓ PDF invoice generation with barcode
✓ Wallet payment system functional
✓ Multi-language support (Arabic/English)
✓ Comprehensive audit logging
✓ Zero critical bugs in testing phase
✓ Documentation complete
✓ System performance < 2 second response time
✓ 99% uptime in testing

# 2. High-Level Roadmap (10 Weeks)

The project is divided into 6 phases with clear milestones and deliverables.
Each week has specific tasks, deliverables, and success criteria.

| Week | Phase | Key Deliverables | Status |
| --- | --- | --- | --- |
| 1-2 | Phase 1: Foundation | Database, Auth, JWT, Project Setup | ⏳ Upcoming |
| 3-4 | Phase 2: Backend (Part 1) | User, Customer, Product APIs | ⏳ Upcoming |
| 5 | Phase 2: Backend (Part 2) | Sales, Invoice, Wallet APIs | ⏳ Upcoming |
| 6 | Phase 3: Frontend | React UI, Login, Dashboard | ⏳ Upcoming |
| 7 | Phase 4: Integration | API-Frontend Integration, Testing | ⏳ Upcoming |
| 8-9 | Phase 5: Optimization | Performance, Security Hardening | ⏳ Upcoming |
| 10 | Phase 6: Go-Live | Final Testing, Documentation | ⏳ Upcoming |
| Post | Maintenance | Bug Fixes, Monitoring | ⏳ Planning |
| Post | Phase 2 Planning | Multi-Tenant, Cloud Deployment | ⏳ Planning |
| Post | Phase 3 Planning | Mobile App, Advanced Analytics | ⏳ Planning |

# 3. Phase 1: Foundation (Weeks 1-2)

## 3.1 Objectives

Setup complete development environment on Windows

Configure database and tables

Implement authentication system (JWT)

Create base Spring Boot project structure

Establish coding standards and CI/CD basics

## 3.2 Weekly Tasks

### Week 1: Setup & Database

Install JDK 17, Maven 3.8.1, PostgreSQL 15

Create D:\erp-system project folder

Configure pom.xml with all dependencies

Create database schema and tables

Setup application.properties configuration

Create base ErpApplication.java

### Week 1 Deliverables:

✓ Complete development environment setup

✓ PostgreSQL database (erp_db) created

✓ All tables with indexes and relationships

✓ Spring Boot project building successfully

✓ Maven dependencies resolved

### Week 2: Authentication & Security

Implement JWT token provider

Create User entity and UserRepository

Build AuthController with login endpoint

Setup Spring Security configuration

Implement password hashing and validation

Test authentication flow in Postman

Create error handling and exception classes

### Week 2 Deliverables:

✓ JWT authentication fully working

✓ Login API endpoint functional

✓ User registration (optional, for admin)

✓ Token refresh mechanism

✓ Role-based access control framework

✓ Security configuration complete

### Phase 1 Milestone:

✅ MILESTONE 1: Foundation Complete
System can start, users can authenticate, database is operational

# 4. Phase 2: Core Backend Development (Weeks 3-5)

## 4.1 Objectives

Build all core entities and repositories

Implement business logic in service layer

Create REST API endpoints for all modules

Implement wallet and payment system

Build tax and accounting logic

Create data validation and error handling

## 4.2 Weekly Tasks

### Week 3: Master Data (Customers & Products)

Create Customer entity with all fields

Create Product entity with SKU and pricing

Build CustomerRepository interface

Build ProductRepository interface

Implement CustomerService with business logic

Implement ProductService with validation

Create CustomerController with CRUD endpoints

Create ProductController with CRUD endpoints

Test all endpoints in Postman

### Week 3 Deliverables:

✓ Customers CRUD API working

✓ Products CRUD API working

✓ Data validation on input

✓ Search/filter functionality

✓ All endpoints tested and documented

### Week 4: Sales & Invoicing Module

Create SalesOrder entity

Create SalesOrderItem entity

Create SalesInvoice entity

Build sales repositories

Implement invoice creation logic

Implement tax calculation (14% VAT)

Create invoice APIs

Implement PDF generation (iText)

Create barcode generation (ZXing)

### Week 4 Deliverables:

✓ Sales order creation working

✓ Invoice generation with tax calculation

✓ PDF download functional

✓ Barcode generation in invoices

✓ Receipt format for POS printers

✓ Email invoice delivery (basic)

### Week 5: Wallet & Accounting

Create Wallet entity

Create WalletTransaction entity

Implement wallet charging logic

Implement wallet debit on purchase

Create ChartOfAccounts entity

Create JournalEntry entity

Implement auto-journal entry from sales

Create wallet endpoints

Create accounting report endpoints

### Week 5 Deliverables:

✓ Wallet system fully operational

✓ Payment processing working

✓ Accounting entries auto-generated

✓ Journal entries visible in API

✓ Basic financial reports

✓ All backend APIs complete

### Phase 2 Milestone:

✅ MILESTONE 2: Backend Complete
All APIs functional, database operations working, invoices generating

# 5. Phase 3: Frontend Development (Week 6)

## 5.1 Objectives

Create React application with basic UI

Implement login and authentication

Build main dashboard

Create forms for data entry

Implement API integration

Add multi-language support (Arabic/English)

## 5.2 Weekly Tasks

### Week 6: React Setup & Core UI

Create React project with Create React App

Install required libraries (axios, react-router)

Setup JWT token storage (localStorage)

Create Login component

Create Dashboard component

Create navigation/menu

Build responsive layout

Implement API service calls

Add error handling and loading states

Setup i18n for Arabic/English

### Week 6 Deliverables:

✓ React application running on localhost:3000

✓ Login page functional

✓ Dashboard displaying basic info

✓ API integration working

✓ Multi-language switching (Arabic/English)

✓ Responsive design on desktop

### Phase 3 Milestone:

✅ MILESTONE 3: Frontend Ready
React application can login, authenticate, and display data

# 6. Phase 4: Integration & Testing (Week 7)

## 6.1 Objectives

Complete frontend-backend integration

Implement all core business workflows

Perform comprehensive testing

Fix bugs and optimize performance

Implement logging and monitoring

## 6.2 Weekly Tasks

Create Customer List & Add Customer pages

Create Product List & Add Product pages

Create Create Invoice page (most important)

Integrate PDF download on frontend

Create Wallet management page

Create Reports/Dashboard pages

Perform unit testing of services

Perform integration testing (API + UI)

Test complete invoice creation workflow

Test payment processing workflow

Performance testing and optimization

### Week 7 Deliverables:

✓ All major workflows tested

✓ Invoice creation working end-to-end

✓ Payment processing functional

✓ PDF generation in browser

✓ Multi-language working throughout

✓ Error handling and validation

✓ Performance metrics acceptable

### Phase 4 Milestone:

✅ MILESTONE 4: System Integration Complete
Full system working: login → create invoice → payment → report

# 7. Phase 5: Optimization & Hardening (Weeks 8-9)

## 7.1 Objectives

Performance optimization (backend & frontend)

Security hardening

Code refactoring and cleanup

Comprehensive documentation

Load testing and stress testing

## 7.2 Weekly Tasks

### Week 8: Performance & Security

Database query optimization (indexes, joins)

API response time optimization

Frontend bundle optimization

Implement caching strategies

Security audit of authentication

SQL injection prevention verification

XSS protection verification

CSRF token implementation if needed

Password policy enforcement

SSL/TLS setup for HTTPS

### Week 9: Testing & Documentation

Load testing (50+ concurrent users)

Stress testing (system limits)

Security penetration testing (basic)

All CRUD operations testing

Edge case testing

Browser compatibility testing

Mobile responsiveness testing

Backup and recovery testing

Create technical documentation

Create user manual

### Phase 5 Milestone:

✅ MILESTONE 5: Production Ready
System optimized, secured, tested, documented

# 8. Phase 6: Finalization & Go-Live (Week 10)

## 8.1 Objectives

Final bug fixes and polish

User acceptance testing (UAT)

Deploy to production environment

Setup monitoring and alerting

Provide training to users

Establish support procedures

## 8.2 Weekly Tasks

Final code review and cleanup

Fix any remaining bugs

Prepare production deployment

Setup production database backups

Configure production environment variables

Deploy backend application

Deploy frontend application

Smoke testing in production

User training session

Hand off to support team

Go-Live announcement

### Week 10 Deliverables:

✓ Production application live

✓ All systems operational

✓ Monitoring and alerts active

✓ Backups running automatically

✓ Documentation complete

✓ Support procedures established

✓ Training completed

### Phase 6 Milestone:

✅ MILESTONE 6: SYSTEM LIVE 🎉
ERP System in production, users trained, support ready

# 9. Milestone Tracking & Success Criteria

| Milestone | Target Week | Key Deliverable | Success Criteria | Status |
| --- | --- | --- | --- | --- |
| M1: Foundation | Week 2 | Auth & DB | ✓ Login working | ⏳ |
| M2: Backend | Week 5 | All APIs | ✓ 100+ endpoints | ⏳ |
| M3: Frontend | Week 6 | React App | ✓ UI functional | ⏳ |
| M4: Integration | Week 7 | E2E Working | ✓ Full workflow | ⏳ |
| M5: Production | Week 9 | Optimized | ✓ Performance OK | ⏳ |
| M6: Live | Week 10 | Go-Live | ✓ Users training | ⏳ |

# 10. Risk Management & Contingency

## 10.1 Identified Risks

### Technical Risks

Database Performance [High]: Optimize queries early, implement caching

PDF Generation Complexity [Medium]: Use proven iText library, test early

JavaScript Framework Learning [Medium]: Start React early, use templates

### Schedule Risks

Single Developer Bottleneck [High]: Plan extra time for reviews, automate testing

Scope Creep [Medium]: Stick to MVP, defer Phase 2 features

Dependency Issues [Low]: Manage Maven carefully, test environment

### Business Risks

User Requirements Change [Medium]: Frequent communication, documentation

Data Migration Issues [Low]: Plan migration scripts early

Performance Not Meeting Goals [Medium]: Benchmark early, optimize continuously

## 10.2 Contingency Plans

If Behind Schedule:
1. Defer secondary features to Phase 2
2. Focus on core functionality only
3. Extend timeline by 1-2 weeks if needed
4. Reduce testing scope (automate more)

If Technical Issues:
1. Switch to alternative libraries if needed
2. Simplify features rather than delay
3. Get expert consultation if critical
4. Document workarounds clearly

If Performance Issues:
1. Implement caching immediately
2. Optimize database queries
3. Reduce UI responsiveness requirements if needed
4. Scale infrastructure (add resources)

# Project Summary

| Total Duration | 10 weeks (May 28 - Aug 6, 2026) |
| --- | --- |
| Team Size | 1 Full-Stack Developer |
| Milestones | 6 major milestones |
| Modules | 6 core modules |
| API Endpoints | 50+ REST endpoints |
| Database Tables | 15+ tables |
| Lines of Code | ~10,000 LOC backend + ~5,000 LOC frontend |
| Test Coverage | Unit + Integration testing |
| Documentation | Complete API, user manual, troubleshooting |
| Go-Live Date | Week 10 (August 6, 2026) |

## Next Steps

Confirm roadmap with stakeholders

Setup development environment (Week 0)

Begin Phase 1 implementation

Weekly status meetings on Thursdays

Track progress against milestones

--- Project Roadmap Complete ---
Ready for Execution